## Sayfa1
No | Reviewed Material ID | Section | Page | Line/ No | Error Type | Importance | Explanation | Correction Status | Correction Explanation
1 | I | 6. Assessment | 4 | N/A | 8 | Medium | No assessment is provided for iteration 3 | Under Review
2 | N | N/A | 3 | N/A | 4 | Little | In iteration 4 plan, "iteration 3 plan" header is used. | Under Review
3 | W | N/A | N/A | 65 | 6 | Medium | Although UC-7(Manage Notifications) are taken into iteration 3 plan, in Work Items List document, this work item is stated to be moved to iteration 4 | Under Review
4 | W | N/A | N/A | 71 | 6 | Medium | Although UC-7(Manage Notifications) is stated to be done in iteration 4, work item "Produce test cases for UC-3, UC-4, UC-5, UC-7, UC-9 and do tests and produce test logs" is stated as closed | Under Review
5 | W | N/A | N/A | 96 | 6 | Medium | Although UC-7(Manage Notifications) is stated to be done in iteration 4, it is assigned to iteration 3 | Under Review
6 | W | N/A | N/A | 73 | 8 | Little | Tasks are not assigned | Under Review
7 | D | N/A | 1 | 1 | 9 | Medium | The document does not have a version history, headers and footers, ToC, cover page, etc. In the previous review, the same feedback was provided and it was accepted as to be added in iteration 3. | Under Review
8 | D | N/A | 1 | 1 | 9 | Important | Accepted items in the previous review are not applied. | Under Review
9 | D | N/A | 1 | 1 | 9 | Important | Use Cases are not realized | Under Review
10 | A | N/A | 1 | 1 | 9 | Medium | The document does not have a version history, ToC, and cover page | Under Review
11 | A | 2. Architectural goals and philosophy | 1 | 9 | 8 | Medium | No solid goals were defined nor a set of philosophies were formulated to address these goals. In the previous review, the same feedback was provided and it was accepted as to be added in iteration 3. | Under Review
12 | TS | N/A | N/A | N/A | 8 | Important | Test scripts of use cases 3, 4, 5, 7 and 9 are missing | Under Review
13 | TC | N/A | N/A | N/A | 8 | Important | Test cases of use cases 3, 4, 5, 7 and 9 are missing | Under Review