## Revision History
Version | Description | Author | Date
0.1 | Draft | - Tuğçe Sözer | 2023-03-29
0.2 | Review and add work items | - Ezgi Özkan | 2023-03-30
0.3 | Review and add work items | - Kadir Kılıçoğlu | 2023-03-30
1.0 | Publish | - Ezgi Özkan - Kadir Kılıçoğlu - Tuğçe Sözer | 2023-04-02
2023-01-01 | Update work items as completed for iteration 2 Work items are assigned to iteration 3 | - Tuğçe Sözer | 2023-04-24
2023-02-01 | Update iteration 3 items as back-end work | - Kadir Kılıçoğlu | 2023-05-11
2023-03-01 | Update work items as completed for iteration 3 Work items are assigned to iteration 4 New work items are added as backlog (36,37,38,39,40,41) | - Tuğçe Sözer | 2023-05-14

## Work Items
Vendomatic Work Items List
# | Name/Description | Type | Priority | Size Estimate (Points) | State | Target Iteration | Assignned To | Effort Estimate Left (Hours) | Hours Worked (Total) | Reference Material
1 | Produce draft glossary | Documentation | 1 | 1 | Completed | 1 | - Project Manager - Quality Assurance - Business Analysts - Developers | 0 | 2 | Requirements > Glossary.pdf
2 | Produce draft vision | Documentation | 1 | 3 | Completed | 1 | - Business Analysts | 0 | 10 | Requirements > Vision.pdf
3 | Produce draft system-wide requirements | Documentation | 1 | 5 | Completed | 1 | - Business Analysts | 0 | 24 | Requirements > System-Wide Requirements Specification.pdf
4 | Produce draft use case model | Documentation | 1 | 2 | Completed | 1 | - Business Analysts | 0 | 10 | Requirements > Use Case Model.pdf
5 | Produce draft use cases | Documentation | 1 | 5 | Completed | 1 | - Business Analysts | 0 | 24 | Requirements > Use Cases.pdf
6 | Produce draft risk list | Documentation | 1 | 5 | Completed | 1 | - Project Manager | 0 | 24 | Project Management > Risk List.pdf
7 | Produce draft work item list | Documentation | 1 | 2 | Completed | 1 | - Project Manager | 0 | 8 | Project Management > Work Items List.pdf
8 | Produce iteration plan for iteration 1 and 2 | Documentation | 1 | 2 | Completed | 1 | - Project Manager | 0 | 10 | Project Management > Iteration Plan.pdf
9 | Produce draft project plan | Documentation | 1 | 2 | Completed | 1 | - Project Manager | 0 | 8 | Project Management > Project Plan.pdf
10 | Rough determination of the overall technology stack for the project | Meeting | 1 | 5 | Completed | 1 | - Developers | 0 | 48 | N/A
11 | Research of suitable technologies for frontend
12 | Research of suitable technologies for backend
13 | Blue print for the sytem architecture
14 | Finalize vision document | Documentation | 1 | 1 | Completed | 1 | - Business Analysts | 0 | 2 | Requirements > Vision.pdf
15 | Update glossary | Documentation | 5 | 1 | Completed | 2 | - Project Manager - Quality Assurance - Business Analysts - Developers | 0 | 1 | Requirements > Glossary.pdf
16 | Update system-wide requirements | Documentation | 3 | 1 | Completed | 2 | - Business Analysts | 0 | 2 | Requirements > System-Wide Requirements Specification.pdf
17 | Update use case model | Documentation | 2 | 1 | Completed | 2 | - Business Analysts | 0 | 5 | Requirements > Use Case Model.pdf
18 | Update use cases | Documentation | 2 | 1 | Completed | 2 | - Business Analysts | 0 | 5 | Requirements > Use Cases.pdf
19 | Update risk list | Documentation | 3 | 1 | Completed | 2 | - Project Manager | 0 | 2 | Project Management > Risk List.pdf
20 | Update work item list | Documentation | 5 | 1 | Completed | 2 | - Project Manager | 0 | 2 | Project Management > Work Items List.pdf
21 | Produce iteration plan for iteration 3 | Documentation | 1 | 2 | Completed | 2 | - Project Manager | 0 | 10 | Project Management > Iteration Plan.pdf
22 | Update project plan | Documentation | 2 | 1 | Completed | 2 | - Project Manager | 0 | 2 | Project Management > Project Plan.pdf
23 | Prepare infrastructure | Implementation | 3 | 5 | Completed | 2 | - Developers | 0 | 52
24 | Create backend infrastructure |  |  |  | Completed
25 | Create frontend infrastructure |  |  |  | Completed
26 | Integration of backend and frontend |  |  |  | Completed
27 | Implementation of Login to Web Application | Implementation | 1 | 3 | Completed | 2 | - Quality Assurance - Business Analysts - Developers | 0 | 24 | Web Application
28 | Implementation of Register to the Mobile Application | Implementation | 1 | 3 | Completed | 2 | - Quality Assurance - Business Analysts - Developers | 0 | 24 | Mobile Application
29 | Implementation of Login to Mobile Application | Implementation | 1 | 3 | Completed | 2 | - Quality Assurance - Business Analysts - Developers | 0 | 24 | Mobile Application
30 | Backend Implementation of Manage Operators | Implementation | 1 | 4 | Completed | 3 | - Quality Assurance - Business Analysts - Developers | 0 | 32 | Web Application
31 | Backend Implementation of Manage Vending Machines | Implementation | 1 | 4 | Completed | 3 | - Quality Assurance - Business Analysts - Developers | 0 | 32 | Web Application
32 | Backend Implementation of Manage Products | Implementation | 1 | 4 | Completed | 3 | - Quality Assurance - Business Analysts - Developers | 0 | 32 | Web Application
33 | Backend Implementation of Manage Inventory | Implementation | 1 | 4 | Completed | 3 | - Quality Assurance - Business Analysts - Developers | 0 | 32 | Web Application
34 | Backend Implementation of Search/Filter Products and Vending Machines | Implementation | 1 | 5 | Assigned | 4 | - Quality Assurance - Business Analysts - Developers | 40 | 0 | Mobile Application
35 | Backend Implementation of Rate Products and Vending Machines | Implementation | 1 | 5 | Assigned | 4 | - Quality Assurance - Business Analysts - Developers | 40 | 0 | Mobile Application
36 | Frontend Implementation of Manage Operators | Implementation | 1 | 4 | Backlog |  | - Quality Assurance - Business Analysts - Developers | 32 | 0 | Web Application
37 | Frontend Implementation of Manage Vending Machines | Implementation | 1 | 4 | Backlog |  | - Quality Assurance - Business Analysts - Developers | 32 | 0 | Web Application
38 | Frontend Implementation of Manage Products | Implementation | 1 | 4 | Backlog |  | - Quality Assurance - Business Analysts - Developers | 32 | 0 | Web Application
39 | Frontend Implementation of Manage Inventory | Implementation | 1 | 4 | Backlog |  | - Quality Assurance - Business Analysts - Developers | 32 | 0 | Web Application
40 | Frontend Implementation of Search/Filter Products and Vending Machines | Implementation | 1 | 4 | Backlog |  | - Quality Assurance - Business Analysts - Developers | 32 | 0 | Mobile Application
41 | Frontend Implementation of Rate Products and Vending Machines | Implementation | 1 | 4 | Backlog |  | - Quality Assurance - Business Analysts - Developers | 32 | 0 | Mobile Application